SMART INDIA HACKATHON  ·  48-HOUR SPRINT  ·  TEAM BRIEF v2

QFleet — Team Execution Brief

Quantum-Inspired Green Fleet Optimization

Hours are relative to the start of the clock (H+0); wall-clock times assume a 10:00 Friday start. Write your team members’ names against the roles before circulating.

WHAT CHANGED IN V2 Team Lead and the Deployment / QA / Pitch role are now one person — Kunal. Backend and models are built first; the frontend returns as Phase 3, with two members switching onto it once the API is stable. Roles are re-cut so all five members are on backend work from hour one.

# Where the project stands

| Already done | Still to build |
| --- | --- |
| - Backend: 23 endpoints, all returning real computed results - 4 solvers on a real fleet model with 5 hard constraints - Prediction model: R² 0.9912, MAPE 5.4% - Realistic fleet: 20 Indian-flag vessels, 16 real trade lanes - 135 passing tests | - Quantum tuning endpoint (feature selection + hyperparameters) - Response caching + a sub-3-second demo preset - Statistical benchmark: 10 seeds × 4 algorithms × 3 sizes - Frontend (Phase 3) - Docker, deployment, backup video, deck |

# Phases

| # | Phase | Hours | Clock | Done when |
| --- | --- | --- | --- | --- |
| 0 | Lock the baseline | H+0–3 | Fri 10:00–13:00 | Everyone running the same code, tests green, demo script v0 written, branches cut |
| 1 | Backend + models core | H+3–18 | Fri 13:00–Sat 04:00 | Quantum tuning, caching, demo preset and the statistical benchmark all landed on main |
| 2 | API freeze | H+18–20 | Sat 04:00–06:00 | Endpoints and response shapes locked so the frontend can be built against them |
| 3 | Frontend + hardening | H+20–32 | Sat 06:00–18:00 | M3 and M4 build the UI; M1, M2, M5 harden, document and chart |
| 4 | Integrate, deploy, pitch | H+32–40 | Sat 18:00–Sun 02:00 | One public URL, backup video recorded, deck done, rehearsals 1 and 2 run |
| 5 | Freeze & drill | H+40–45 | Sun 02:00–07:00 | Code freeze, Q&A drilling, rest rotation, final rehearsal |
| 6 | Present | H+45–48 | Sun 07:00–10:00 | Smoke test, hardware check, pitch |

WHY THE API FREEZE AT H+18 MATTERS A frontend built against an API that is still moving is the classic way to lose six hours at 3 a.m. Nothing about request or response shapes changes after H+20 without the lead’s approval — solver internals can keep improving, the contract cannot.

# Who does what

Names to be filled in. Phase 1 is backend for everyone; the Phase 3 column is where each person goes once the API freezes.

|  | Role | Phase 1 (backend, H+3–18) | Phase 3 onward (H+20+) |
| --- | --- | --- | --- |
| M1 | Optimisation & Solvers | Response caching on /optimize keyed to the request body; tune a demo preset that finishes under 3 s; profile the solver hot path | Performance fixes found in rehearsal; write the one-page "what is quantum-inspired" technical note |
| M2 | ML & Prediction | Wire the unused QPSO feature selector and hyperparameter tuner into train_model.py --tune and an endpoint; 5-fold CV | Validation charts, model card, and the prediction slides |
| M3 | Benchmarking & Statistics | 10 seeds × 4 algorithms × 3 fleet sizes; export mean ± std for objective, hypervolume, IGD, runtime to CSV | Switches to frontend — charts and the results pages |
| M4 | Data & Domain Modelling | Extend the fleet registry, refine scenario economics (abatement cost, retrofit capex), impact-at-scale analysis | Switches to frontend — layout, forms and the plan table |
| M5 | API, Testing & Docs | Endpoint hardening, test coverage, OpenAPI descriptions and examples, a Postman collection | Stays backend: keeps main green, fixes whatever the frontend surfaces |

# Kunal — Lead, Architect, Deployment, QA & Presenter

YOUR JOB THIS WEEKEND You are not writing the most code. You are keeping main green, keeping five people unblocked, cutting scope early enough that it does not hurt, making sure the demo happens even if everything fails, and telling the story at the end. Every hour you spend deep in one feature is an hour nobody is steering.

| Window | What you do | Done when |
| --- | --- | --- |
| H+0 – H+1 | Kickoff. Hand out this brief, walk the timeline, confirm each person’s first task and definition of done. Tag baseline-sih, set the branch strategy. | Five people working inside the first hour |
| H+1 – H+3 | Write demo script v0 before anyone builds. Eight minutes, click by click, with what you say over each screen. Circulate it. | Everyone builds toward one known demo — the highest-leverage hour of the 48 |
| H+3 – H+8 | Docker + docker-compose for the backend while integrating branches as they land. Keep the test suite green. | docker compose up works from a clean clone; no branch older than four hours |
| H+8 – H+12 | Deploy the API to a public URL (Render / Railway). Set QGF_CORS_ORIGINS for the frontend that is coming. | A public link that answers /api/health from a phone on mobile data |
| H+12 – H+13 | First scope cut. Say out loud what will not finish. Stand-up, then hand over the night watch. | A written, announced scope decision |
| H+13 – H+19 | Rest. You are presenting — non-negotiable. | Six hours of sleep |
| H+19 – H+20 | Declare the API freeze. Publish the locked endpoint contract to M3 and M4 before they start the frontend. | Frozen contract in the shared folder |
| H+20 – H+26 | Record the backup demo video of the working backend. Then full QA sweep on the deployed URL — every endpoint, logged with severity. | A video that could replace the live demo and still win; a triaged bug list |
| H+26 – H+32 | Build the deck: twelve slides. Problem, why it is hard, approach, architecture, demo placeholder, results, benchmark, impact, roadmap, team, ask. | Real numbers throughout, no placeholders |
| H+32 – H+36 | Integrate the frontend. Rehearsal 1 with the full team — run it end to end without stopping, then debrief. | Honest timing and a list of what broke |
| H+36 – H+40 | Fix round, then Rehearsal 2. Second scope cut if needed. Re-record the video if the UI changed the demo. | Inside the time limit, twice |
| H+40 – H+41 | Q&A drilling — have the team fire the hardest questions, especially "is this actually quantum". Declare code freeze. | No question can surprise you; freeze enforced |
| H+41 – H+45 | Rest four hours. Two alarms. | You present rested — this beats one more fix |
| H+45 – H+48 | Hardware check: HDMI adapter, charger, hotspot, offline build, video on USB. Rehearsal 3. Present. | Everything verified in venue conditions |

# Scope-cut ladder

Decided in advance so the call is arithmetic, not an argument at 3 a.m. Cut from the top when behind.

- Frontend polish → ship a plain, functional UI; judges forgive plain, not broken

- Frontend entirely → demo from Swagger UI at /docs, which already works and needs no build

- Statistical benchmark depth → 3 seeds instead of 10; still honest, still reportable

- Quantum tuning result → fall back to the default model, which is already at R² 0.99

- Public deployment → localhost on the presenting laptop plus the backup video

- Never cut: a working backend, the backup video, the rehearsals, your own sleep.

# The three answers that decide the jury round

- "Is this actually quantum?" No, and say so. Quantum-inspired: QPSO samples positions from a delta potential well instead of using velocity; QGA encodes chromosomes as qubit registers with rotation gates. Classical hardware. The assignment sub-problem is a QUBO, so real annealing is roadmap, not demo. Overclaiming here loses the round.

- "Your Pareto front is tiny." Fuel, CO₂ and cost are strongly correlated — the genuine trade-off surface is narrow, and widens at fuel-choice boundaries. Better a small honest front than padding with dominated points.

- "Classical PSO beats your quantum solver in your own benchmark." On a scalarised objective, sometimes yes, and we publish it. QPSO wins on front diversity and hypervolume. Here is the 10-seed table with standard deviations.

# Top risks

| Risk | Owner | Mitigation |
| --- | --- | --- |
| Frontend starts against a moving API | Kunal | Hard API freeze at H+18, contract published before any UI work begins |
| Frontend not finished by rehearsal 1 | M3 / M4 | Swagger UI at /docs is a working fallback demo from hour zero |
| Live run slow on stage | M1 | Demo preset under 3 s, response caching, pre-computed fallback results |
| Venue Wi-Fi or laptop fails | Kunal | Public URL + local stack + phone hotspot + video on a USB stick |
| Merge conflicts late in the run | Kunal | Integrate every four hours; no branch lives longer than that |
| Presenter exhausted | Kunal | Four hours’ sleep before the pitch, no exceptions |

REMEMBER The backend already works, is tested, and produces real numbers. What separates teams now is whether the demo runs without stuttering, whether the story lands in the first ninety seconds, and whether you answer hard questions without flinching.